May 5, 2026

SR 60 from 1 mile west of Peavine Rd to Florida’s Turnpike

State Road Number:	60

Section Number:	92070-000

County:	Osceola

Project Limits:	1 mi west of Peavine Rd to the west side of the SR 91 (Florida’s Turnpike) overpass bridges

MP:	MP 10.937 to 20.261 (9.324 MI)

FM: 	456132-1

| - Existing R/W Map Project Numbers: | 443702-1 (2022); MP 5.216 to MP 13.400, 50-ft LT & RT 239685-2 (2001); MP 19.973 to MP 21.820, var (50-ft min) LT & RT 9207-201 (1956); MP 14.129 to MP 21.820, var (33-ft min) LT & RT 92070 (1924); MP 0.000 to MP 21.820, var (33-ft min) LT & RT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Old Construction Project Numbers: | 450623-1 (2026); MP 20.261 to MP 21.820, Pavement Only Resurf 445697-1 (2023); MP 4.800 to MP 19.540), AVT 441036-1 (2021); MP 19.548 to MP 20.418, Traffic Ops Impr 428867-1 (2014); MP 1.229 to MP 19.956, Milling & Resurfacing 419124-1 (2009); MP 0.113 to MP 19.950, SAPM 239685-2 (2005); MP 20.290 to MP 21.820, Widening 239756-1 (2001); MP 8.114 to MP 16.040, Milling & Resurfacing 239740-1 (1999); MP 16.040 to MP 20.21, Milling & Resurfacing 92070-3510 (1995); MP 1.229 to MP 16.040, Passing Lanes 92070-3512 (1992); MP 0.113 to MP 19.603, Paved Shoulders 92070-3508 (1986); MP 8.000 to MP 15.973, Milling & Resurfacing 92070-3506 (1984); MP 15.973 to MP 21.828, Milling & Resurfacing 92070-3501 (1964); MP 1.183 to MP 15.148, Lane Widening 9207-108 (1956); MP 15.178 to MP 21.820, Reconstruction 9207-106 (1954); MP 15.200 to MP 22.161, Widening 9207-901 (1949); MP 0.000 to MP 22.364, Surface Treatment 9207-104 (1947); MP 0.000 to MP 22.820, New Construction |  |  |  |  |  |  |
| - Additional R/W required? | No. |  |  |  |  |  |  |
| - Level of Community Awareness Plan: | Level 2, rural resurfacing with widening. |  |  |  |  |  |  |
| - Agreements required? | ☐ No |  |  |  | ☒ Yes |  |  |
|  | ☐ Yes, including Local Funds. |  |  |  |  |  |  |
| - Are there any bridges within the limits? | #920199 SR 60 WB over SR 91 (Florida’s Turnpike) #920200 SR 60 EB over SR 91 (Florida’s Turnpike) |  |  |  |  |  |  |
| - Are there any RR Crossings within the project limits or in the vicinity? | No. |  |  |  |  |  |  |
| - Are there any Airports within 10 nautical miles? | Yes. |  |  |  |  |  |  |
| - Storm Water Management jurisdiction: | SFWMD & SJRWMD. SJRWMD is anticipated to be the permitting lead on this project. |  |  |  |  |  |  |
| - Is the Project within the CCCL (Coastal Construction Control Line)? | No. |  |  |  |  |  |  |
| - Existing Utilities: (per SS1C, as-builts, and field markers) | AT&T Corp/PEA (Transmission/Long Distance) AT&T Florida Bright House Networks LLC dba Charter/Spectrum CenturyLink/Level 3 CenturyLink/Lumen Crown Castle Fiber Florida Southeast Connection, LLC. Peace River Electric Cooperative, Inc. |  |  |  |  |  |  |
| - Any special MOT concerns? | Coordinate temporary lane closures near ramps with FTE. |  |  |  |  |  |  |
| - Any construction concerns? | High seasonal groundwater levels. |  |  |  |  |  |  |
| - Design/Posted/Target Speeds (mph): | Location (MP) | Design Speed |  | Posted Speed |  | Target Speed |  |
|  | 10.937 to 19.000 19.000 to 19.303 19.303 to 20.148 20.148 to 20.261 | 65 65 45 55 |  | 60 45 45 45 |  | N/A N/A N/A N/A |  |
| - Design Criteria and Context Classification: | SHS, FDM (2026), SIS |  |  |  |  |  |  |
|  | Location (MP) |  | Context Classification |  |  |  | Access Class |
|  | 10.937 to 19.662 19.662 to 20.261 |  | C2 “Rural” C3R “Suburban Residential”* |  |  |  | 03 03 |
| - Lump Sum or Pay Item? | Pay Item. |  |  |  |  |  |  |
| - Proposed Design Schedule: | 24-30 Months. Environmental analysis and permitting. |  |  |  |  |  |  |

*The Preliminary Context Classification for this location is defined as C3R “Suburban Residential”; however, based on the guidance and criteria within the FDOT Context Classification Guide this area appears to fall into C2T “Rural Town” more appropriately.

# Local Agency Coordination:

Conduct a Stakeholder meeting during the design phase to confirm the proposed scope remains consistent with the expectations set during scoping, close the loop on what will be included in the project, and learn of any changes that may have occurred since the Scope’s development.

An agreement will be needed if work is required within Osceola County's Right of Way.  The Engineer shall coordinate to obtain an agreement with the County for maintenance related to proposed improvements.

# Project Location Map: (Google Maps Link)

BEGIN PROJECT

BEGIN PROJECT

Project Abstract

Rural asphalt milling and resurfacing project with sections of widening to increase the separation between opposing travel lanes.

Project Abstract

Rural asphalt milling and resurfacing project with sections of widening to increase the separation between opposing travel lanes.

END PROJECT

END PROJECT

The Engineer is responsible for verifying all items in the proposed scope and shall review the project for conformance with all applicable criteria and standards.

# Intent and Nature of Project:

The purpose of the project is to rehabilitate the asphalt pavement to extend the service life of the existing roadway and provide segments of widening to increase separation between opposing travel lanes, including other necessary roadside improvements, in accordance with FDOT Design Manual Section 114 .  The project is based on an initial request from the FDOT District 5 Pavement Management and Maintenance Office to rehabilitate the pavement from the beginning of the passing lane at MP 13.028 to east of Justin Rohde Rd at MP 14.301.

The Scope was subsequently expanded at the request of the District Intermodal Services Department to include rehabilitation of the pavement from 1 mile west of Peavine Rd to east of the bridges over SR 91 (Florida’s Turnpike), MP 10.937 to MP 20.261, eliminate the 2-lane passing zones and replace them with a widened section providing a 2-ft buffered centerline between opposing travel lanes.  Passing will only be permitted in the 3-lane sections upon completion of this project.

- The Concept and Scope are provided to convey the general overall intent of the project and to establish the estimated cost for programming.  These are not intended to serve as detailed design level directives but are to communicate the project’s primary objectives as approved by District staff.  The Engineer is responsible for developing the final design within the constraints of the projects budget.

# Project Description:

- Project is in southern Osceola County in the vicinity of Yeehaw Junction.

- SR 60 is classified as a rural principal arterial is a designated SIS corridor and an evacuation route per the Florida Division of Emergency Management.

- The following projects have been identified within the vicinity of this project.  The FDOT PM is to confirm the status, proposed improvements, and coordinate project limits prior to advertisement.

  - FPID: 423374-2 SR 91/Florida’s Turnpike widening project PD&E is currently in development.  The project includes the evaluation of widening SR 91 (Florida’s Turnpike) from SR 70 to SR 60 and new interchange locations.  The FTE PM is Ronald Kareiva.

  - FPID: 443702-1 SR 60 passing lane project is currently under construction and anticipated to be completed in Fall 2026.  The project includes the construction of EB and WB passing lanes along SR 60 from Blanket Bay Slough to 1 mile west of Peavine Rd and includes milling and resurfacing and widening of the roadway.  There is an exception of milling and reconstruction work between MP 8.315 to MP 9.590.  The end limit of the milling and widening will represent the begin project limit for this project.  The FDOT PM is Blaire Scheller.

  - FPID: 450623-1 SR 60 POP project is currently under construction and anticipated to be completed in Spring 2026.  The project includes friction course only milling and resurfacing of SR 60 from SR 91 (Florida’s Turnpike) to the Indian River County Line.  The begin limit of the milling and resurfacing will represent the end project limit for this project.  The FDOT PM is Blaire Scheller.

  - FPID: 452574-1 SR 60 PD&E project is currently in development.  The project includes the evaluation of widening the SR 60 from two to four lanes and safety improvements along the corridor.  The FDOT PM is Maria Serrano-Acosta.

  - FPID: 454213-1 SR 60 RRR project is currently under scope development and anticipated to be let for construction in 2029.  The project includes the resurfacing, widening, and signing and pavement markings improvements of SR 60 from the Kissimmee River Bridge to east of the S-65A Access Rd.  There is an exception of work between MP 6.986 to MP 8.265.  The FDOT PM is Jude Jean-Francois.

# Typical Sections:

- Per as-built plans, SR 60 includes 4 typical sections.  Changes are proposed as described below:

  - MP 10.937 to MP 13.030, MP 14.300 to MP 14.770, and MP 16.040 to MP 19.603: 2-lane undivided flush shoulder roadway with 12-ft travel lanes and 6-ft shoulders (4-ft paved).  Dimensions noted are per the original SPN: 92070-3512 shoulder construction plans which are consistent with the field conditions.  Subsequent resurfacing projects FPID: 239756-1 and FPID: 428867-1 indicate 10-ft total shoulders.  The 4-ft paved shoulders are consistent across projects.

    - This typical will be modified to provide a two lane undivided flush shoulder roadway with 12-ft travel lanes, 10-ft WB shoulder (5-ft paved) and maintaining the 6-ft EB shoulder (4-ft paved) with a 2-ft buffer between the EB and WB travel lanes.  Widening is to be along the WB travel lanes only and will tie in at the existing passing lane areas and just west of SR 15/US 441/S Kenansville Road.

  - MP 13.030 to MP 14.300 and MP 14.770 to MP 16.040: 3-lane undivided flush shoulder roadway with two 12-ft travel lanes, one 12-ft passing lane, and 8-ft shoulders (4-ft paved).  Dimensions noted are per the original SPN: 92070-3510 shoulder construction plans which are consistent with the field conditions.  Subsequent resurfacing projects FPID: 239756-1 and FPID: 428867-1 indicate 10-ft total shoulders.  The 4-ft paved shoulders are consistent across projects.  No changes are proposed.

  - MP 19.603 to MP 19.994: 3-lane undivided flush shoulder roadway with two 12-ft travel lanes, one 12-ft two-way left turn lane, and 8-ft shoulders (5-ft paved).  No changes are proposed.

  - MP 19.994 to MP 20.261:  4-lane divided flush shoulder roadway with four 12-ft travel lanes, 8-ft inside shoulders (variable width paved), 15.5-ft outside shoulders (8-ft shoulder pavement & shoulder gutter) separated by a 64-ft grassed median.  No changes are proposed.

- Based on 2025 Traffic Data:

| MP | TMS Site No. | AADT | T% |
| --- | --- | --- | --- |
| 19.439 | 920058 | 11,400 | 26.9 |
| 19.712 | 920027 | 14,800 | 32.5 |

# Roadway Scope Items:

- A Pavement Condition Assessment has been requested and will be completed by FDOT.  By observation the pavement is in fair condition with moderate longitudinal cracking, rutting, and alligator cracking in the wheel paths.  Prepare five pavement designs: 1) milling and resurfacing all travel lanes, 2) milling and resurfacing paved shoulders, 3) friction course-only milling and resurfacing of paved shoulders, 4) full-depth widening of two-lane segments, and 5) deeper rehabilitation of the travel lanes.

  - Adjacent widening projects utilize underdrain systems and underdrain installation may be warranted depending on base-clearance conditions encountered.

  - Project qualifies for smoothness class.

- The existing unpaved shoulder is generally in fair to good condition with isolated locations of poor condition that is readily correctible utilizing Standard Plans Index 570-010.  For LRE purposes 10% was assumed to require correction.

  - The following locations were noted as having abnormal wear to the existing unpaved shoulder which requires restoration:

    - MP 11.895 Peavine Rd eastbound

    - MP 19.603 SR 15/US 441/S Kenansville Rd eastbound and within the SW quadrant.

- MPSV data will be requested and made available when received.  The Engineer is to review the data, determine survey needs, and gain consensus with the District prior to initiating design.  Some cross slope correction and overbuild is anticipated.

  - The superelevation of 2 curves were noted to be deficient.  Correction is anticipated.

- Evaluate the existing roadway guardrail for conformance to current Standards and design criteria; reset and replace as needed to correct deficiencies.  Guardrail meeting the 2013 Design Standards are to remain.  For LRE purposes, 20% of the guardrail is assumed to be reset.

  - Install new slope guard guardrail between the SR 91 (Florida’s Turnpike) overpass bridges #920199 and #920200.

- MP 10.937 to MP 13.061 and MP 14.247 to MP 14.784 and MP 16.002 to MP 19.544 LT:  Remove the existing paved shoulder and provide an additional 7-ft of full depth pavement and 5-ft unpaved shoulders.  Additional roadside improvements incidental to this widening include:

  - Reconstruct the driveway connections at the following locations [next page]:

    - MP 11.368 LT

    - MP 11.895 LT & RT (Peavine Rd)

    - MP 16.632 LT, (Mae Bass Rd)

    - MP 17.727 LT

    - MP 18.932 LT

    - MP 18.957 LT

    - MP 19.319 LT: Coordinate with the property owner to determine if the existing driveway should be replaced or eliminated.  The Right of Way fence currently prohibits access.

    - MP 19.336 LT

    - MP 19.417 LT

    - MP 19.550 LT:  Coordinate with the property owner of the demolished lot within the NW quadrant of the intersection to determine any future development for driveway replacement to accommodate the widening.

  - MP 17.964: Remove the existing guardrail and provide new guardrail to accommodate the widening and box culvert extension.

- MP 11.895 Peavine Rd: Provide an eastbound left turn lane to Peavine Rd.  Several vehicles were observed waiting to turn, the shoulder is worn from passing stopped vehicles, and there is a crash history at the intersection.

- MP 19.936 LT: Sight line from existing driveway to upstream traffic is blocked from overgrown vegetation.  Clear the vegetation provide sufficient intersection sight distance.

# Drainage Scope Items:

- Based on field observations the existing roadside drainage system appears to be functioning properly except as noted below:

  - The condition of several cross and side drains could not be verified due to high water levels and heavy vegetation.  All roadside ditches should be cleared and rehabilitated.  Confirm condition of existing side drains and reconstruct as needed.

  - Depressional areas and voids in the paved and unpaved shoulders at cross drain locations is indicative of a potential pipe joint leaking or other culvert issue were identified.  Include a field survey with cross drain analysis to determine options for repair or replacement.  Receive concurrence from the District prior to initiating design.  Reconstruction has been assumed for estimating purposes.  Condition has been forwarded to the District Drainage Office for consideration in advance of this project.  Confirm status prior to design.

    - MP 11.665

    - MP 12.723

    - MP 17.059

  - MP 15.178 LT:  Reconstruct the existing 15-in damaged and non-functional side drain.

- The primary goal for improvement along this corridor is to utilize the existing drainage systems where feasible. Modify the existing drainage systems as needed to accomplish the roadway improvements.

  - Update ditch drainage design including capacity calculations for longitudinal grade adjustments and flow changes corresponding to roadway improvements.

  - Underdrain installation may be warranted due to base clearance conditions encountered.

  - Reconstruct all side drains to align with regraded ditches and reconstructed driveway connections.

  - MP 11.895 LT (Peavine Rd):  Existing cross drain is silted and requires extension to accommodate the proposed roadway widening.  Reconstruct the headwall and extend the existing pipes (3 x 24-in), and maintain flow of existing roadside ditches.

  - MP 14.250 to MP 14.300 LT: Remove and reconstruct the existing underdrain.

  - MP 14.602 LT:  Based on as-built plan information, the cover over the existing 2 x 30-in cross drain may be insufficient to accommodate the proposed widening.  Verify cover and provide sufficient clearance to culvert.

  - MP 17.964:  Extend the existing double 8-ft x 5-ft box culvert to accommodate the proposed roadway widening.

  - Proposed widening occurs within four existing ditch block systems and existing underdrain systems (SPN 92070-3510).  Evaluate systems for new impervious and widening geometry, modify as needed in accordance with water quantity and water quality requirements.

- Floodplain impacts within FEMA Zone A are anticipated based on the proposed improvements. Widen existing ditch sections within the Right of Way to create additional storage volume, thereby offsetting encroachments and providing the required floodplain compensation area.

# Utility Scope Items:

- Adjust all valve covers, utility pull boxes, fire hydrants, etc. to be flush with roadside, roadway pavement, etc. as necessary to complete the proposed improvements.

  - Avoid conflicts with Florida Southeastern Connection facilities.

- Quality Level A “QL A” utility information is anticipated.  Construction activities that involve underground work within proximity to noted utilities include road widening, culvert reconstruction/extension, and lighting relocation.

  - Due to the proximity of overhead facilities, adjustment, relocation, and/or temporary de-energization may be required.

- The Engineer is to confirm utility poles and above ground utility features are shown on all applicable plan sheets for the purpose of utility coordination.

- Any underground work must be Vvh’d.  Complete the Vvh’s and show any potential conflicts in the plans prior to the Phase II plans ERC submittal.

- Evaluate offsets to existing utilities, including guy wires, anchors, etc. in areas of widening and the proposed edge of travel shift.  Relocation and/or adjustments may be required.

# Multimodal Scope Items:

## The Engineer shall include a project-specific pedestrian/bicyclist temporary traffic control plan.

## Transit:

- There are no public transportation routes within the project limits.

## Bicycles:

- The existing 4-ft paved shoulder and keyholes serve as the bicycle facility.  No changes proposed.

Pedestrians:

- There are no existing pedestrian facilities throughout the project corridor.  No changes proposed.

# Permitting Scope Items:

- Coordinate with FDOT, submitting a permit determination letter to the Environmental Permits Office, Attention District Five Permits Coordinator, for review and concurrence during the design process, considering the below descriptions of work and conditions.

  - This project is anticipated to exceed one acre of soil disturbing activities and will require NPDES coverage under the FDEP Generic Permit for Stormwater Discharge from Large and Small Construction Activities.

  - Some project areas may qualify as an exempt activity, but there are existing permitted systems; modifications are anticipated.

  - An assessment of permitting requirements should be performed, including which provisions under the New Stormwater Rule apply.

  - Note that this project is within both the South Florida and St. John’s Water Management District’s.

# Environmental Scope Items:

- Recent PD&E documentation and coordination is available to supplement these efforts.

- Complete an environmental assessment:

  - A protected species assessment is required for the project.  The level of assessment should be commensurate with the scope of work.  The assessment should focus on species applicable to the project area with consideration given to consultation areas, habitats, and known occurrence data.

    - The project is within the Audubon’s Crested Caracara and Grasshopper Sparrow’s habitat range.  However, per preliminary discussions with the District, species specific surveys are not anticipated based on the improvements being contained within the FDOT Right of Way and previous determinations by the regulatory agencies.

  - Wetlands were noted within the Right of Way throughout the project limits and are to be identified by an environmental assessment.  The apparent wetland lines shown on the Concept are from the Florida Geographic Data Library and are for informational purposes only.  Impacts are anticipated.

  - There are floodplains adjacent to the project.  The current scope of work is anticipated to have impacts and coordination with the FDOT Environmental Permits Office will be required.  Floodplain compensation is anticipated to be achieved within the existing Right of Way.

  - A contamination assessment is required for the project.  The level of documentation required will be dependent on the contamination sites in the area, scope of work proposed, and previous assessments conducted.  Coordinate with the District Contamination Impact Coordinator to determine project needs.

    - Contamination sites have been identified.

  - Cogon grass was observed on the corridor and does not appear to be under treatment.  A note directing the Contractor’s attention to this is to be included in the plans.

- A Cultural Resources Assessment is required and is to be conducted by Cultural Resources Professionals as outlined in 36 CFR Part 61 and set forth in the Professional Qualifications Standards section of the Secretary of the Interior’s Standard and Guidelines for Archaeology and Historic Preservation.

# Structural Scope Items:

- MP 17.964 LT:  Extend the existing double 8-ft x 5-ft concrete box culvert to accommodate the proposed widening.  Provide structural design, analysis and detailing to ensure adequate reinforcement, connections, and differential settlement compensation.

# Traffic Operations (Includes Signing, Signals, ITS) Scope Items:

## Signing and Pavement Markings

- Signing and pavement markings shall be completed for the project limits.  Inventory all signing including evaluation for compliance with all applicable criteria and coordinate with the District Design Office for any changes to existing signing.  Any existing signs that conflict with the proposed signs or pavement markings, or non-compliant signs or pavement markings, are to be addressed in the plans.

  - A No Passing Zone study is not required; this project is to provide a 2-ft buffer between travel lanes to ensure all 2-lane segments are no passing zones.

  - Complete calculations for 8 multi-post sign relocations or replacements.

  - This project qualifies for lane departure mitigation thru application of Audible and Vibratory Treatment based on the posted speed equal or greater than 50 mph and flush shoulder typical section.

  - Relocate or replace all signage on the north side of the two-lane segments to accommodate the widening as necessary including the solar powered flashing beacon warning signs.  Replace non-compliant signage on the south side as necessary.

  - In pavement “SPEED LIMIT” and "SLOW DOWN" markings have been added along SR 60 between approximately MP 15.8 and MP 17.6 and are to be replaced in kind.

  - Install road terminal signs at the following T-intersections in accordance with FDOT Standard Plans 700-109:

    - MP 14.235 Justin Rohde Rd

    - MP 15.575 Rohde Rd

    - MP 16.632 Mae Bass Rd

## Signals

- Signal detection is to be reestablished.   Existing detection methods are provided within the table for each signal.

- Complete analysis and plan detailing for the modification of the existing strain poles at SR 60 and SR 15/US 441/S Kenansville Road as described in the tables below.

- The project includes 2 signalized intersections.

| MP 19.603 – SR 15 (US 441/Kenansville Rd) (Diagonal Span Strain Pole) |  |
| --- | --- |
| Detection | Video detection. |
| Backplates | One existing for WB 4-section. Provide flexible retroreflective for all. |
| Left Turns | EB, NB & SB permissive, WB 4-section protected-permissive. |
| Pedestrian Signals | N/A |
| Other | Existing intersection lighting to remain. Provide internally illuminated strain pole mounted street name signs. Existing poles are to remain. |

| MP 19.994 – To/From NB Florida’s Turnpike Ramps (Box Span Strain Pole) |  |
| --- | --- |
| Detection | Video detection. |
| Backplates | Existing reflectorized to remain. |
| Left Turns | EB 4-section protected-permissive, SB protected-only. |
| Pedestrian Signals | N/A |
| Other | Existing intersection lighting to remain. FTE maintains the traffic signals and equipment. |

- There are 2 Traffic Monitoring Sites within the project’s construction limits.  Coordinate disposition with the District Data Collection Manager.

  - 920058 PTMS:  Site is within limits of proposed widening.  Reconstruct if the site is to remain.

  - 920027 PTMS:  Work is limited to the removal of site or restoration of detection if the site is to remain.

## Intelligent Transportation Systems (ITS)

- Modifications are to be consistent with the ITS Master Plan.  The Engineer:

- Shall follow the Risk Assessment protocol, including Checklist and Systems Engineering analysis.

- Shall designate fiber in the plans, determine any conflicts and resolve.

- Additional ITS guidance can be found here:

https://www.cflsmartroads.com/technical_docs.html

- MP 11.862 LT:  An existing solar powered CCTV camera west of Peavine Rd will be in conflict with the proposed widening.  Remove and relocate.

# Lighting Scope Items:

- There is intermittent roadway lighting within the project limits at the following locations:

  - MP 11.706 to MP 12.084 LT (wood pole mounted luminaires)

  - MP 19.540 to MP 19.994 RT (standard lighting)

  - MP  19.994 to MP 20.190 LT (standard lighting)

- MP 11.706 to 12.084 LT (Peavine Rd):  Existing wood pole intersection lighting was installed by Peace River Electric Co under a Roadway Illumination Service Agreement (RISA) in 2025.  Coordinate relocation to accommodate proposed widening.  Relocation is assumed to be accomplished through an updated RISA.

# Landscaping Scope Items:

- No work.

# Surveying and Mapping Scope Items:

# Design Survey

- Provide 3D Topographic Survey for the areas and locations of identified and proposed improvements shown on the Concept.  Total survey area will be determined by the Engineer based on their needs for design.

  - Survey should include all above ground surface features, including, but not limited to valve covers, overhead utilities, meter boxes, manholes, etc.

  - Include items identified by the environmental assessment.

  - Include drainage structures and nearest connecting structures shall be detailed within the survey areas only, unless otherwise instructed.

- Provide quality level A “QL A” Sub-surface Utility Engineering (SUE) and survey thereof for the areas and locations of identified and proposed improvements shown on the Concept.  Total SUE limits will be determined by the Engineer based on the limits of disturbance.

  - Vvh’s are anticipated.  Coordinate with the Engineer for anticipated number of Vvh’s required for the project.

- Obtain Level 2 Survey for areas where cross slope and superelevation correction is recommended, including the pavement surfaces, unpaved shoulders, and ditch/roadside slopes.

Right of Way Mapping

- Establish the existing Right of Way for the areas and locations of proposed improvements based upon the best available evidence.  The level of effort for this task will be unique for each project based on the proposed design and nature of the corridor.

  - Establishing existing Right of Way will be challenging due to the scarcity of identifiable corners and age of the Maps.  Mobile LiDAR may be required to obtain accurate surface data, with the centerline of pavement used as a computed baseline to support Right of Way determination.

- Establish a computed survey baseline (baselines if needed) and provide to the Engineer for their plans. Stationing should be adjusted to be different than any historic alignment, as it should not be misconstrued as a retracement of the existing alignment.

# Office of Right of Way Scope Items:

- Work outside the apparent FDOT Right of Way but within public Right of Way of Peavine Rd for drainage modifications at the intersection.  Limits of the public Right of Way on Peavine Rd as shown in the Concept were based on property record information and will need to be verified.

# Geotechnical and Pavement Scope Items:

- FDOT to perform Pavement Coring Report and provide ESAL calculation and Resilient Modulus values.

- Perform and obtain the necessary geotechnical information as directed by the Geotechnical Office:

- Soil boring(s) to support roadway widening and box culvert extension.

- Soil boring(s) to support the box culvert extension.

# Design Documentation:

- The design documentation items noted below are necessary to implement the proposed improvements.  The Engineer is responsible for verifying all items in the proposed Scope and design conform with all applicable criteria and standards, including the identification of any required Memoranda, Variations and Exceptions.

The Engineer is responsible for reviewing crash data for conformance to FDM 114 and applicability to required design documentation: Memoranda, Variations and Exceptions.

- Design Variation Memorandum

- Vertical Curve Length- Per FDM Table 210.10.4, the minimum allowable vertical curve length for a sag vertical curve along a roadway with a design speed of 55 mph is 250-ft.  Based on the existing as-built profile from FM# 239685-2 the existing sag vertical curve length is 157-ft.  To provide sufficient vertical curve length the roadway profile would need to be adjusted before and after the existing curve and require reconstruction between the existing bridge and signalized intersection.  The improvements for this project are limited to resurfacing in this area and reconstruction is not recommended.  The Engineer is to review and analyze the crash history at this location.

- Design Variation

  - Diagonal Span Wire Assembly- Per FDM 232.9, diagonal span assemblies may only be used for flashing beacon installations.  A design variation is required for any other diagonal installation.  Modifications are proposed to provide backplates on existing signal heads provided there is sufficient structural capacity to do so.  The Engineer is to review and analyze the crash history at this location.

- Design Exception

  - Stopping Sight Distance- Per FDM 210.11.1 Table 210.11.1 and AASHTO, the minimum allowable stopping sight distance for a 55 mph design speed roadway with a 5 percent downgrade is 541-ft and 495-ft, respectively.  Based on the existing as-built profile from FM# 239685-2 the crest vertical curve at PI MP 20.214 provides approximately 474-ft of stopping sight distance.  The existing crest vertical curve provides a K value of 98; however, based on FDOT RRR criteria and AASHTO the minimum K value for crest vertical curves should be 114.  To provide sufficient stopping sight distance would require reconstruction of the roadway through the intersection at SR 60 and the NB On and Off Ramps to/from Florida's Turnpike and is not recommended under this project.  A design exception is required to maintain the deficient stopping sight distance.  The Engineer is to review and analyze the crash history at this location.

# Additional Items Considered During Scoping:

- Consideration was given to constructing guardrail to provide protection from roadside hazards including concrete culvert headwalls and multi-post signs that would fall within the new construction clear zone.  Existing Right of Way is insufficient to accommodate modifications outside of the new construction clear zone and protection would be required.  Due to the nature of the improvements being minor roadside widening to accommodate safety improvements it was determined that new construction criteria could not be met.  Roadside items that fall outside of the RRR clear zone are to remain.

- Per FDM Table 210.4.1 12-ft full width shoulders should be considered with high truck traffic (>10%).  Wider shoulders are limited by Right of Way, environmental, and drainage constraints and cannot be accommodated on this project.

- Areas of widening impact locations of existing ditch block systems.  Based on the proposed widening, typical direct impacts to the ditch blocks are not anticipated.  Reconstruction of the ditch blocks were considered but are not accounted for within the project cost estimate.

- Preliminary analysis of floodplains and wetlands was based on best available GIS information.  A typical section approach was utilized to determine the order of magnitude of the impacts to determine if mitigation is feasible within the project corridor without the need for additional Right of Way.

- Discussions for preferred method of AVT were on-going at the time of scoping.  Final disposition to be determined in design.