## Risk Register
456596-1 US 192 at Old Town Pedestrian Crossing Candidate Safety Project No Letting Date
Active/Closed | Category | Risk Description | Current Status | Date Last Updated | Risk to Schedule | Risk to Estimate | Risk to Scope | Stakeholder Involvement | Notes/Tracking Comments
Active | Transit | LYNX Schedule |  |  | Low | Low | Low | Yes | Consideration should be given to the LYNX 30-minute headway schedule along the US 192 corridor.
Active | Traffic Ops | Future mast arms/ Future full intersection signal |  |  | Med | Med | Med | Yes | District Traffic Operations requested signal configuration to consider future fully signalized intersection.
Active | Traffic Ops | Signal spacing |  |  | Low | Low | Low | No | Proposed pedsignal is within the influence of adjacent signalized intersection.
Active | Traffic Ops | I-4 construction detours |  |  | Low | Low | Med | Yes | Adjacent construction projects intend to utilize US 192 for temporary lane closures.
Active | Geotechnical | Poor soil conditions anticipated |  |  | Med | High | Low | No | Poor soil conditions have been identifed requiring special design.

## Sample Risk Factors
Some Sample Risk Factors - this is not an expansive list of all risk on projects
FGT Involvement
Utilities located in easements
Fatalities that occur during design
Political or heavy stakeholder involvement
Consultant team staffing changes
TIP/STIP Amendments
Design changes that require re-evaluation of PD&E
Changes that increase permitting effort
Adjacent permit projects or development during design/construction
Railroad involvement
Work adjancent to ROW where old ROW maps exist
Extended review times by external stakeholders
Contributing funding uncertainty (LF, safety, TOs, etc)
Maintaining public support throughout the life of the project (including construction)
Contamination on the project
Muck or high ground water table, unsuitables
Changes to or interpretation of permitting criteria
Unresponsive external stakeholder
Subconsultant staffing shortage or delay
4F involvement
Species - any surveys needed at specific times of the year, any protected
Any new innovations, processes, products
Changes in pay items or specs
Proprietary products
Design life expectancy or aging infrastructure (box culverts, clay pipes, brick structures, signals, etc)
Lane closure restrictions, special events, etc.
Staging opportunities for the contractor; affecting MOB/MOT.